## Initiatives
ID | Name | Category | Stage | RAG | RAG Commentary | Progress % | Owner | Start | Target End | Last Updated
00000000-0000-0000-0000-000000000221 | Finance shared services | Operational Improvement | plan | green |  | 46 | Grace Oyelaran | 2026-02-15 | 2027-02-28 | 2026-08-17T10:44:25.024Z
00000000-0000-0000-0000-000000000220 | Supply chain redesign | Risk Reduction | assess | red | Critical supplier resilience assumptions are unresolved. | 24 | Faisal Rahman | 2026-05-01 | 2027-04-30 | 2026-08-17T10:44:24.997Z
00000000-0000-0000-0000-000000000211 | Digital self-service portal | Customer Experience | plan | amber | Content ownership and release acceptance are not yet stable. | 42 | Carmen Ortiz | 2026-03-01 | 2027-01-15 | 2026-08-17T10:44:24.969Z
00000000-0000-0000-0000-000000000210 | Supplier payment terms renegotiation | Cost Reduction | realise | green |  | 86 | Aisha Khan | 2025-10-01 | 2026-08-31 | 2026-08-17T10:44:24.937Z
00000000-0000-0000-0000-000000000209 | Workforce rebalancing - Ops | Cost Reduction | execute | red | Consultation sequencing and transition capacity are materially off track. | 54 | Grace Oyelaran | 2026-01-08 | 2026-10-31 | 2026-08-17T10:44:24.910Z
00000000-0000-0000-0000-000000000208 | Customer Data Platform rollout | Revenue Growth | identify | green |  | 18 | Faisal Rahman | 2026-06-01 | 2027-03-31 | 2026-08-17T10:44:24.882Z
00000000-0000-0000-0000-000000000207 | Billing system retirement | Risk Reduction | plan | amber | Supplier exit terms are not yet agreed and data migration windows are tight. | 47 | Emma Lindqvist | 2026-03-15 | 2027-01-31 | 2026-08-17T10:44:24.854Z
00000000-0000-0000-0000-000000000206 | Support centre automation | Operational Improvement | assess | green |  | 30 | Carmen Ortiz | 2026-04-01 | 2027-02-28 | 2026-08-17T10:44:24.827Z
00000000-0000-0000-0000-000000000205 | Cloud migration - Phase 1 | Operational Improvement | execute | amber | Identity integration and migration factory capacity are behind plan. | 68 | David Chen | 2026-02-01 | 2026-12-18 | 2026-08-17T10:44:24.783Z
00000000-0000-0000-0000-000000000204 | Procurement consolidation - indirect spend | Cost Reduction | plan | green |  | 62 | Aisha Khan | 2026-01-15 | 2026-11-30 | 2026-08-17T10:44:24.743Z

## Value Lines
Initiative | Name | Type | Category | GL Account | Cost Centre | Currency | Target | Forecast | Actual | State
Procurement consolidation - indirect spend | Indirect supplier run-rate saving | cost_out | Procurement |  |  | GBP | 6200000 | 5450000 | 900000 | forecast_approved
Cloud migration - Phase 1 | Legacy hosting cost removal | cost_out | Technology run cost |  |  | GBP | 2400000 | 2000000 | 500000 | draft
Support centre automation | Support handling effort release | non_financial | FTE hours |  |  | GBP | 18000 | 14500 | 1200 | draft
Billing system retirement | Legacy billing licence avoidance | cost_out | Technology run cost |  |  | GBP | 1700000 | 1250000 | 0 | draft
Customer Data Platform rollout | Cross-sell conversion uplift | revenue_up | Growth |  |  | GBP | 3300000 | 2750000 | 250000 | draft
Workforce rebalancing - Ops | Operations labour saving | cost_out | Labour |  |  | GBP | 4800000 | 3100000 | 600000 | draft
Supplier payment terms renegotiation | Working capital benefit | one_off | Payment terms |  |  | GBP | 5500000 | 5200000 | 4900000 | booked
Digital self-service portal | Avoided assisted-service contacts | cost_out | Service operations |  |  | GBP | 1900000 | 1400000 | 150000 | draft
Supply chain redesign | Inventory and expedite cost reduction | cost_out | Supply chain |  |  | GBP | 3900000 | 2100000 | 0 | draft
Finance shared services | Transactional finance productivity | cost_out | Shared services |  |  | GBP | 2250000 | 1850000 | 200000 | forecast_approved

## Audit
Occurred At | Actor | Entity Type | Entity ID | Action | Hash